## Project Plan
Task No. | Task | Subtask | Effort in Days | Start | End | Predecessors | Resources
1 | Literature Review | Paper Selection | 5 | 25th Janury | 30th January
2 |  | Paper Reading | 7 | 31st January | 7th February
3 |  | Paper Comprehension | 7 | 8th February | 15th February
4 |  | Paper Methodology Summary | 7 | 16th February | 23rd February
5 |  | Paper Results Summary | 7 | 24th February | 3rd March
6 |  | Documenting | 7 | 24th February | 3rd March |  | Check proposal references
7 | Dataset | Dataset Selection | 5 | 4th March | 9th March
8 |  | Data Cleaning | 5 | 10th March | 15th March
9 |  | Data Pre-processing | 14 | 16th March | 8th April
10 |  | Data Visualization | 14 | 25th March | 8th April
11 |  | Statistical Analysis | 14 | 25th March | 8th April
12 |  | Documenting | 1 | 25th March | 26th March |  | Kaggle.com
13 | Machine Learning | Desired Output | 7 | 27th March | 4th April
14 |  | Available Tools | 7 | 5th April | 12th April
15 |  | Algorithm Intent | 7 | 13th April | 20th April
16 |  | Coding | 7 | 21st April | 26th April
17 |  | Documenting | 7 | 21st April | 26th April |  | 6, 12
18 | Software for 2FA | Requirements Analysis | 5 | 27th April | 2nd May
19 |  | Mockups | 5 | 3rd May | 8th May
20 |  | Database ER | 5 | 3rd May | 8th May
21 |  | Code Implementation | 14 | 9th May | 22nd May
22 |  | Documenting | 5 | 17th May | 22nd May |  | 6, 12, 17
23 | Final Report | Combining All Documentations | 5 | 17th May | 22nd May |  | 6, 12, 17, 22

## Gantt Chart
Start | Sum of Effort in Days
10th March | 5
13th April | 7
16th February | 7
16th March | 14
17th May | 10
21st April | 14
24th February | 14
25th Janury | 5
25th March | 29
27th April | 5
27th March | 7
31st January | 7
3rd May | 10
4th March | 5
5th April | 7
8th February | 7
9th May | 14

## Known Risks
Risk Type | Risk Event | Likelihood (1-10) | Impact (1-10) | Risk Value (1-10) | Risk Monitoring | Risk Management
P | Availability of Researcher | 7 | 8 | 56 |  | Schedule Regular Meeting
S | Availability of Computer Resources | 3 | 9 | 27 |  | Arrange for Backup Systems
T | Data Loss | 1 | 9 | 9 |  | Data Backup Scheduling
P | Unavailability of Data | 8 | 7 | 56 |  | Experimental Data/Change Data Source
F | May Require Financial Investment for Machine Learning | 6 | 5 | 30 |  | Make Available a Small Budget
Legend
| Risk Types |  | Control Flags
| P | People |  | Medium Risk
| S | Security |  | Low Risk
| T | Technology |  | Acceptable Risk
| F | Financial